## template_to_consider
Project duration problem (PERT/CPM model)
Input Parameters | [8 empty] | Activity C
| Activity A |  |  |  | Activity B
[8 empty] | Probability | Cumulative Probability | Time |  | Activity D
Probability | Cumulative Probability | Time |  | Probability | Cumulative Probability | Time |  | 0.1 | 0 | 10
0.25 | 0 | 5 |  | 0.2 | 0 | 3 |  | 0.25 | 0.1 | 12 | Probability | Cumulative Probability | Time
0.35 | 0.25 | 6 |  | 0.55 | 0.2 | 5 |  | 0.4 | 0.35 | 14 | 0.6 | 0 | 8
0.25 | 0.6 | 7 |  | 0.25 | 0.75 | 7 |  | 0.2 | 0.75 | 16 | 0.4 | 0.6 | 10
0.15 | 0.85 | 8 | [5 empty] | 0.05 | 0.95 | 18
|  | Activity A |  | Activity B |  | Activity C |  | Activity D | PROJECT
TRIAL | Rand # | duration of A | Rand # | duration of B | Rand # | duration of C | Rand # | duration of D | DURATION |  | Summary Statistic
1 | 0.7111 | 7 | 0.31154 | 5 | 0.10873 | 12 | 0.51005 | 8 | 32 |  | Estimate of avg length |  |  | 34.05
[11 empty] | Standard deviation |  |  | 2.9244
[8 empty] | Trial 1 | 32 |  | Minimum |  |  | 28
[8 empty] | Trial 2 | 32 |  | Maxium |  |  | 43
[8 empty] | Trial 3 | 32 |  | Probability completed <=36 |  |  | 81.67%
[8 empty] | Trial 4 | 37
[8 empty] | Trial 5 | 34
[8 empty] | Trial 6 | 35
[8 empty] | Trial 7 | 33
[8 empty] | Trial 8 | 34
[8 empty] | Trial 9 | 37
[8 empty] | Trial 10 | 37
[8 empty] | Trial 11 | 36
[8 empty] | Trial 12 | 28
[8 empty] | Trial 13 | 32
[8 empty] | Trial 14 | 33
[8 empty] | Trial 15 | 43
[8 empty] | Trial 16 | 36
[8 empty] | Trial 17 | 32
[8 empty] | Trial 18 | 33
[8 empty] | Trial 19 | 28
[8 empty] | Trial 20 | 32
[8 empty] | Trial 21 | 36
[8 empty] | Trial 22 | 33
[8 empty] | Trial 23 | 34
[8 empty] | Trial 24 | 35
[8 empty] | Trial 25 | 36
[8 empty] | Trial 26 | 35
[8 empty] | Trial 27 | 40
[8 empty] | Trial 28 | 35
[8 empty] | Trial 29 | 37
[8 empty] | Trial 30 | 35
[8 empty] | Trial 31 | 32
[8 empty] | Trial 32 | 30
[8 empty] | Trial 33 | 34
[8 empty] | Trial 34 | 35
[8 empty] | Trial 35 | 36
[8 empty] | Trial 36 | 35
[8 empty] | Trial 37 | 38
[8 empty] | Trial 38 | 38
[8 empty] | Trial 39 | 36
[8 empty] | Trial 40 | 30
[8 empty] | Trial 41 | 39
[8 empty] | Trial 42 | 33
[8 empty] | Trial 43 | 38
[8 empty] | Trial 44 | 35
[8 empty] | Trial 45 | 28
[8 empty] | Trial 46 | 35
[8 empty] | Trial 47 | 39
[8 empty] | Trial 48 | 29
[8 empty] | Trial 49 | 39
[8 empty] | Trial 50 | 35
[8 empty] | Trial 51 | 40
[8 empty] | Trial 52 | 31
[8 empty] | Trial 53 | 37
[8 empty] | Trial 54 | 34
[8 empty] | Trial 55 | 34
[8 empty] | Trial 56 | 35
[8 empty] | Trial 57 | 31
[8 empty] | Trial 58 | 31
[8 empty] | Trial 59 | 40
[8 empty] | Trial 60 | 33
[8 empty] | Trial 61 | 38
[8 empty] | Trial 62 | 36
[8 empty] | Trial 63 | 37
[8 empty] | Trial 64 | 35
[8 empty] | Trial 65 | 33
[8 empty] | Trial 66 | 40
[8 empty] | Trial 67 | 36
[8 empty] | Trial 68 | 34
[8 empty] | Trial 69 | 28
[8 empty] | Trial 70 | 33
[8 empty] | Trial 71 | 30
[8 empty] | Trial 72 | 32
[8 empty] | Trial 73 | 34
[8 empty] | Trial 74 | 34
[8 empty] | Trial 75 | 35
[8 empty] | Trial 76 | 33
[8 empty] | Trial 77 | 39
[8 empty] | Trial 78 | 34
[8 empty] | Trial 79 | 36
[8 empty] | Trial 80 | 31
[8 empty] | Trial 81 | 36
[8 empty] | Trial 82 | 30
[8 empty] | Trial 83 | 33
[8 empty] | Trial 84 | 36
[8 empty] | Trial 85 | 35
[8 empty] | Trial 86 | 32
[8 empty] | Trial 87 | 32
[8 empty] | Trial 88 | 29
[8 empty] | Trial 89 | 35
[8 empty] | Trial 90 | 29
[8 empty] | Trial 91 | 33
[8 empty] | Trial 92 | 32
[8 empty] | Trial 93 | 34
[8 empty] | Trial 94 | 35
[8 empty] | Trial 95 | 28
[8 empty] | Trial 96 | 30
[8 empty] | Trial 97 | 33
[8 empty] | Trial 98 | 32
[8 empty] | Trial 99 | 36
[8 empty] | Trial 100 | 35
[8 empty] | Trial 101 | 31
[8 empty] | Trial 102 | 34
[8 empty] | Trial 103 | 33
[8 empty] | Trial 104 | 32
[8 empty] | Trial 105 | 35
[8 empty] | Trial 106 | 32
[8 empty] | Trial 107 | 32
[8 empty] | Trial 108 | 34
[8 empty] | Trial 109 | 34
[8 empty] | Trial 110 | 29
[8 empty] | Trial 111 | 32
[8 empty] | Trial 112 | 33
[8 empty] | Trial 113 | 36
[8 empty] | Trial 114 | 37
[8 empty] | Trial 115 | 33
[8 empty] | Trial 116 | 37
[8 empty] | Trial 117 | 35
[8 empty] | Trial 118 | 33
[8 empty] | Trial 119 | 35
[8 empty] | Trial 120 | 34
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
Note on B5: Windows User: The Cumulative Probability column should display the starting value of each interval of random number to be associated with activity time

## PERT_Chart
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.